## Original Dataset
M&E_Record_ID | Project | State | Intervention | Baseline_% | Target_% | Current_Achievement_% | Beneficiaries | Local_Jobs_Created | People_Trained | People_Gaining_Clean_Energy_Access | System_Uptime_% | Community_Satisfaction_5 | Performance_Status | Achievement_Gap_pp | Target_Gap_pp
ME-0001 | Niger Community Power Project | Anambra | Solar Water Pump | 61 | 74 | 85 | 2365 | 27 | 131 | 1681 | 96.8% | 4 | On Track | 24 | -11
ME-0002 | Enugu Clean Energy Project | Edo | Solar Backup System | 63 | 78 | 72 | 1192 | 51 | 37 | 1053 | 94.7% | 4.7 | On Track | 9 | 6
ME-0003 | Niger Community Power Project | Lagos | Community Energy Access | 61 | 78 | 61 | 2328 | 66 | 57 | 2196 | 85.8% | 4.7 | At Risk | 0 | 17
ME-0004 | Edo Community Mini-grid | Enugu | Skills Training | 54 | 77 | 92 | 2012 | 9 | 96 | 1715 | 88.5% | 4.3 | On Track | 38 | -15
ME-0005 | Kwara SME Solar Programme | Kaduna | Skills Training | 37 | 94 | 81 | 1525 | 56 | 241 | 1447 | 88.6% | 3.9 | At Risk | 44 | 13
ME-0006 | Rivers Solar Productive-Use Programme | Delta | Community Energy Access | 37 | 92 | 97 | 151 | 65 | 204 | 139 | 83.4% | 4.8 | On Track | 60 | -5
ME-0007 | Ogun Solar Hub | Cross River | Solar Water Pump | 58 | 74 | 75 | 2040 | 34 | 273 | 1697 | 89.2% | 4.2 | On Track | 17 | -1
ME-0008 | Kwara SME Solar Programme | Abia | Community Energy Access | 71 | 87 | 73 | 355 | 57 | 292 | 267 | 83.1% | 4.8 | At Risk | 2 | 14
ME-0009 | Niger Community Power Project | Kano | Institutional Capacity Building | 37 | 95 | 95 | 1600 | 31 | 208 | 1126 | 88.5% | 3.9 | On Track | 58 | 0
ME-0010 | Ogun Solar Hub | Kaduna | Institutional Capacity Building | 42 | 87 | 96 | 1836 | 16 | 190 | 1212 | 82.4% | 3.8 | On Track | 54 | -9
ME-0011 | Oyo Solar Water Initiative | Kwara | Solar Water Pump | 44 | 78 | 89 | 644 | 55 | 332 | 517 | 96% | 3.5 | On Track | 45 | -11
ME-0012 | Kaduna Health Power | Ogun | Solar Water Pump | 45 | 78 | 72 | 1886 | 15 | 256 | 1299 | 91.1% | 3.7 | On Track | 27 | 6
ME-0013 | Ogun Solar Hub | Kano | Solar Water Pump | 71 | 88 | 78 | 2400 | 35 | 240 | 2279 | 96% | 4.8 | At Risk | 7 | 10
ME-0014 | Rivers Solar Productive-Use Programme | Delta | Solar Backup System | 66 | 82 | 81 | 271 | 57 | 219 | 249 | 83% | 3.8 | On Track | 15 | 1
ME-0015 | Ogun Solar Hub | Oyo | Community Energy Access | 31 | 77 | 71 | 352 | 9 | 166 | 252 | 84.4% | 4.3 | On Track | 40 | 6
ME-0016 | Plateau School Energy Project | Kwara | Solar Water Pump | 33 | 91 | 89 | 2304 | 46 | 183 | 2274 | 78.2% | 4.4 | On Track | 56 | 2
ME-0017 | Enugu Clean Energy Project | Kaduna | Skills Training | 48 | 95 | 83 | 1799 | 31 | 229 | 1793 | 89.6% | 4.9 | At Risk | 35 | 12
ME-0018 | Oyo Solar Water Initiative | Kwara | Solar Backup System | 67 | 81 | 72 | 1002 | 12 | 203 | 860 | 81.2% | 4.8 | At Risk | 5 | 9
ME-0019 | Enugu Clean Energy Project | Oyo | Solar Backup System | 53 | 91 | 99 | 231 | 8 | 214 | 211 | 79.2% | 3.2 | On Track | 46 | -8
ME-0020 | Enugu Clean Energy Project | Anambra | Community Energy Access | 55 | 84 | 87 | 2289 | 53 | 159 | 2216 | 84.7% | 4.4 | On Track | 32 | -3
ME-0021 | Ogun Solar Hub | Plateau | Institutional Capacity Building | 31 | 72 | 59 | 1536 | 65 | 313 | 1365 | 98.4% | 3.4 | At Risk | 28 | 13
ME-0022 | Enugu Clean Energy Project | Kano | Community Energy Access | 34 | 75 | 52 | 954 | 50 | 110 | 931 | 95.7% | 4.2 | Off Track | 18 | 23
ME-0023 | Niger Community Power Project | Kano | Solar Water Pump | 39 | 94 | 98 | 1993 | 56 | 330 | 1547 | 80% | 4.2 | On Track | 59 | -4
ME-0024 | Plateau School Energy Project | Enugu | Solar Mini-grid | 31 | 70 | 58 | 439 | 63 | 326 | 386 | 89.4% | 3.4 | At Risk | 27 | 12
ME-0025 | Oyo Solar Water Initiative | Abia | Community Energy Access | 57 | 95 | 84 | 753 | 34 | 71 | 496 | 89.3% | 3.6 | At Risk | 27 | 11
ME-0026 | Plateau School Energy Project | Lagos | Solar Mini-grid | 71 | 91 | 94 | 1529 | 24 | 228 | 1034 | 97.3% | 4.5 | On Track | 23 | -3
ME-0027 | Ogun Solar Hub | Delta | Solar Mini-grid | 55 | 82 | 77 | 669 | 48 | 281 | 567 | 81.9% | 3.4 | On Track | 22 | 5
ME-0028 | Rivers Solar Productive-Use Programme | Enugu | Community Energy Access | 42 | 86 | 73 | 1348 | 38 | 79 | 932 | 98.1% | 4.4 | At Risk | 31 | 13
ME-0029 | Enugu Clean Energy Project | Niger | Solar Backup System | 34 | 95 | 79 | 1551 | 21 | 292 | 1511 | 96.2% | 3.6 | At Risk | 45 | 16
ME-0030 | Niger Community Power Project | Cross River | Solar Water Pump | 72 | 84 | 76 | 1083 | 38 | 119 | 962 | 98.2% | 3.3 | On Track | 4 | 8
ME-0031 | Oyo Solar Water Initiative | Abia | Community Energy Access | 46 | 76 | 67 | 879 | 39 | 160 | 734 | 89.6% | 3.7 | At Risk | 21 | 9
ME-0032 | Kwara SME Solar Programme | Anambra | Solar Water Pump | 45 | 73 | 66 | 508 | 31 | 256 | 456 | 80.1% | 3.7 | On Track | 21 | 7
ME-0033 | Enugu Clean Energy Project | Ogun | Community Energy Access | 37 | 76 | 85 | 1561 | 21 | 216 | 1441 | 86.6% | 4 | On Track | 48 | -9
ME-0034 | Niger Community Power Project | Rivers | Community Energy Access | 35 | 93 | 100 | 1737 | 7 | 112 | 1685 | 83.4% | 4.6 | On Track | 65 | -7
ME-0035 | Oyo Solar Water Initiative | Plateau | Solar Backup System | 66 | 79 | 66 | 526 | 70 | 125 | 343 | 99% | 4.8 | At Risk | 0 | 13
ME-0036 | Kwara SME Solar Programme | Plateau | Solar Mini-grid | 48 | 74 | 77 | 805 | 73 | 310 | 789 | 86.6% | 4.5 | On Track | 29 | -3
ME-0037 | Kaduna Health Power | Anambra | Solar Mini-grid | 41 | 92 | 64 | 2378 | 76 | 298 | 1600 | 97.1% | 3.9 | Off Track | 23 | 28
ME-0038 | Kwara SME Solar Programme | Plateau | Institutional Capacity Building | 57 | 71 | 57 | 2495 | 28 | 93 | 2405 | 79.8% | 3.9 | At Risk | 0 | 14
ME-0039 | Niger Community Power Project | Plateau | Solar Mini-grid | 43 | 72 | 56 | 2226 | 78 | 30 | 2093 | 98.4% | 3.7 | At Risk | 13 | 16
ME-0040 | Ogun Solar Hub | Ogun | Institutional Capacity Building | 41 | 94 | 93 | 889 | 57 | 291 | 756 | 86.4% | 3.2 | On Track | 52 | 1
ME-0041 | Rivers Solar Productive-Use Programme | Anambra | Solar Mini-grid | 72 | 84 | 88 | 1436 | 7 | 265 | 1206 | 83.9% | 4.4 | On Track | 16 | -4
ME-0042 | Oyo Solar Water Initiative | Cross River | Institutional Capacity Building | 69 | 81 | 69 | 220 | 46 | 36 | 160 | 84.8% | 3.6 | At Risk | 0 | 12
ME-0043 | Oyo Solar Water Initiative | Niger | Community Energy Access | 45 | 73 | 49 | 155 | 33 | 170 | 112 | 94.2% | 3.3 | Off Track | 4 | 24
ME-0044 | Plateau School Energy Project | Oyo | Community Energy Access | 44 | 73 | 62 | 1539 | 22 | 125 | 1112 | 84.4% | 4.7 | At Risk | 18 | 11
ME-0045 | Kwara SME Solar Programme | Delta | Solar Mini-grid | 65 | 71 | 83 | 1029 | 33 | 64 | 790 | 95.3% | 3.6 | On Track | 18 | -12
ME-0046 | Rivers Solar Productive-Use Programme | Kwara | Community Energy Access | 51 | 89 | 76 | 1470 | 39 | 348 | 1073 | 86.8% | 3.6 | At Risk | 25 | 13
ME-0047 | Enugu Clean Energy Project | Plateau | Skills Training | 61 | 73 | 73 | 357 | 61 | 343 | 265 | 79.7% | 4.9 | On Track | 12 | 0
ME-0048 | Niger Community Power Project | Oyo | Skills Training | 71 | 72 | 88 | 1956 | 64 | 114 | 1591 | 91.3% | 3.9 | On Track | 17 | -16
ME-0049 | Edo Community Mini-grid | Anambra | Solar Backup System | 53 | 86 | 100 | 324 | 34 | 126 | 242 | 80.8% | 3.4 | On Track | 47 | -14
ME-0050 | Niger Community Power Project | Cross River | Solar Backup System | 41 | 86 | 82 | 1451 | 68 | 66 | 1049 | 94.5% | 3.6 | On Track | 41 | 4
ME-0051 | Oyo Solar Water Initiative | Anambra | Skills Training | 48 | 95 | 85 | 91 | 70 | 302 | 78 | 91% | 4.4 | At Risk | 37 | 10
ME-0052 | Rivers Solar Productive-Use Programme | Kwara | Institutional Capacity Building | 67 | 94 | 87 | 1199 | 13 | 317 | 877 | 91.4% | 4.5 | On Track | 20 | 7
ME-0053 | Plateau School Energy Project | Abia | Institutional Capacity Building | 51 | 94 | 81 | 1577 | 69 | 31 | 1208 | 88% | 3.2 | At Risk | 30 | 13
ME-0054 | Enugu Clean Energy Project | Kwara | Solar Backup System | 68 | 71 | 79 | 400 | 54 | 143 | 361 | 88.6% | 4.3 | On Track | 11 | -8
ME-0055 | Enugu Clean Energy Project | Ogun | Institutional Capacity Building | 58 | 84 | 81 | 2252 | 27 | 129 | 1534 | 90.9% | 3.8 | On Track | 23 | 3
ME-0056 | Rivers Solar Productive-Use Programme | Kwara | Institutional Capacity Building | 74 | 73 | 78 | 2333 | 64 | 236 | 1767 | 96% | 4.2 | On Track | 4 | -5
ME-0057 | Rivers Solar Productive-Use Programme | Kaduna | Solar Water Pump | 61 | 82 | 69 | 1858 | 73 | 106 | 1569 | 85.4% | 3.4 | At Risk | 8 | 13
ME-0058 | Ogun Solar Hub | Delta | Solar Mini-grid | 73 | 71 | 73 | 2236 | 30 | 123 | 1678 | 84.4% | 4.7 | On Track | 0 | -2
ME-0059 | Plateau School Energy Project | Lagos | Solar Water Pump | 57 | 88 | 97 | 2065 | 48 | 344 | 1623 | 83.2% | 3.4 | On Track | 40 | -9
ME-0060 | Kwara SME Solar Programme | Kaduna | Skills Training | 61 | 80 | 78 | 2038 | 57 | 73 | 1947 | 99.4% | 4.2 | On Track | 17 | 2
ME-0061 | Ogun Solar Hub | Edo | Solar Backup System | 30 | 86 | 93 | 87 | 32 | 131 | 60 | 91.6% | 3.4 | On Track | 63 | -7
ME-0062 | Kwara SME Solar Programme | Kwara | Community Energy Access | 38 | 76 | 71 | 1875 | 22 | 121 | 1279 | 94.8% | 4.3 | On Track | 33 | 5
ME-0063 | Enugu Clean Energy Project | Anambra | Institutional Capacity Building | 74 | 91 | 79 | 937 | 29 | 318 | 700 | 94.6% | 4.3 | At Risk | 5 | 12
ME-0064 | Niger Community Power Project | Anambra | Solar Water Pump | 44 | 92 | 80 | 1882 | 29 | 61 | 1763 | 78.9% | 4 | At Risk | 36 | 12
ME-0065 | Rivers Solar Productive-Use Programme | Kwara | Institutional Capacity Building | 67 | 86 | 90 | 1335 | 75 | 71 | 1208 | 85.8% | 4.3 | On Track | 23 | -4
ME-0066 | Kwara SME Solar Programme | Anambra | Solar Mini-grid | 55 | 75 | 73 | 1981 | 15 | 70 | 1919 | 78.5% | 3.7 | On Track | 18 | 2
ME-0067 | Enugu Clean Energy Project | Plateau | Community Energy Access | 33 | 80 | 78 | 1737 | 14 | 234 | 1609 | 84.8% | 4.2 | On Track | 45 | 2
ME-0068 | Enugu Clean Energy Project | Plateau | Solar Backup System | 58 | 88 | 88 | 2461 | 38 | 305 | 2029 | 80.3% | 3.4 | On Track | 30 | 0
ME-0069 | Kwara SME Solar Programme | Abia | Community Energy Access | 44 | 83 | 76 | 586 | 50 | 200 | 471 | 91.9% | 3.3 | On Track | 32 | 7
ME-0070 | Niger Community Power Project | Niger | Solar Mini-grid | 36 | 91 | 96 | 1952 | 44 | 349 | 1594 | 90.9% | 4.2 | On Track | 60 | -5
ME-0071 | Rivers Solar Productive-Use Programme | Kwara | Solar Water Pump | 62 | 70 | 70 | 1619 | 20 | 151 | 1170 | 79.3% | 4.1 | On Track | 8 | 0
ME-0072 | Edo Community Mini-grid | Abia | Solar Mini-grid | 64 | 77 | 64 | 999 | 39 | 263 | 677 | 90.2% | 4.7 | At Risk | 0 | 13
ME-0073 | Edo Community Mini-grid | Anambra | Skills Training | 58 | 85 | 91 | 2387 | 40 | 36 | 1989 | 84.9% | 4 | On Track | 33 | -6
ME-0074 | Enugu Clean Energy Project | Rivers | Skills Training | 59 | 91 | 88 | 1169 | 15 | 241 | 907 | 84.6% | 3.5 | On Track | 29 | 3
ME-0075 | Ogun Solar Hub | Niger | Solar Backup System | 52 | 95 | 96 | 1815 | 27 | 105 | 1478 | 87.1% | 4.9 | On Track | 44 | -1
ME-0076 | Enugu Clean Energy Project | Lagos | Solar Backup System | 39 | 74 | 61 | 1627 | 30 | 265 | 1106 | 95.5% | 3.7 | At Risk | 22 | 13
ME-0077 | Plateau School Energy Project | Kwara | Solar Backup System | 68 | 90 | 84 | 501 | 40 | 205 | 403 | 79% | 4.6 | On Track | 16 | 6
ME-0078 | Kwara SME Solar Programme | Ogun | Solar Water Pump | 33 | 86 | 68 | 1201 | 25 | 191 | 1173 | 88% | 4 | At Risk | 35 | 18
ME-0079 | Plateau School Energy Project | Cross River | Solar Water Pump | 43 | 76 | 58 | 1734 | 52 | 284 | 1139 | 95.6% | 4.6 | At Risk | 15 | 18
ME-0080 | Plateau School Energy Project | Edo | Solar Backup System | 61 | 79 | 80 | 969 | 18 | 142 | 685 | 82% | 3.5 | On Track | 19 | -1

## Working Dataset
Community Renewable Energy Impact & Performance Analysis
Record_ID | Project | State | Intervention | Baseline_pct | Target_% | Current_Achievement_% | Beneficiaries | Local_Jobs_Created | People_Trained | People_Gaining_Clean_Energy_Access | System_Uptime_% | Community_Satisfaction | Achievement_Gap_pp | Achievement_Gap | Target_Gap | Target_Achievement_Rate | Clean_Energy _Access_Rate | Training-to-Employment_Rate | Beneficiary_Without_Recorded_Clean_Engergy_Access | Performance Status
ME-0001 | Niger Community Power Project | Anambra | Solar Water Pump | 61 | 74 | 85 | 2365 | 27 | 131 | 1681 | 96.8% | 4 | 24 | 24 | 11 | 114.9% | 71.08% | 20.61% | 684 | Meeting/Exceeding Target
ME-0002 | Enugu Clean Energy Project | Edo | Solar Backup System | 63 | 78 | 72 | 1192 | 51 | 37 | 1053 | 94.7% | 4.7 | 9 | 9 | -6 | 92.31% | 88.34% | 137.8% | 139 | Moderately Below Target
ME-0003 | Niger Community Power Project | Lagos | Community Energy Access | 61 | 78 | 61 | 2328 | 66 | 57 | 2196 | 85.8% | 4.7 | 0 | 0 | -17 | 78.21% | 94.33% | 115.8% | 132 | Significantly Below Target
ME-0004 | Edo Community Mini-grid | Enugu | Skills Training | 54 | 77 | 92 | 2012 | 9 | 96 | 1715 | 88.5% | 4.3 | 38 | 38 | 15 | 119.5% | 85.24% | 9.375% | 297 | Meeting/Exceeding Target
ME-0005 | Kwara SME Solar Programme | Kaduna | Skills Training | 37 | 94 | 81 | 1525 | 56 | 241 | 1447 | 88.6% | 3.9 | 44 | 44 | -13 | 86.17% | 94.89% | 23.24% | 78 | Significantly Below Target
ME-0006 | Rivers Solar Productive-Use Programme | Delta | Community Energy Access | 37 | 92 | 97 | 151 | 65 | 204 | 139 | 83.4% | 4.8 | 60 | 60 | 5 | 105.4% | 92.05% | 31.86% | 12 | Meeting/Exceeding Target
ME-0007 | Ogun Solar Hub | Cross River | Solar Water Pump | 58 | 74 | 75 | 2040 | 34 | 273 | 1697 | 89.2% | 4.2 | 17 | 17 | 1 | 101.4% | 83.19% | 12.45% | 343 | Meeting/Exceeding Target
ME-0008 | Kwara SME Solar Programme | Abia | Community Energy Access | 71 | 87 | 73 | 355 | 57 | 292 | 267 | 83.1% | 4.8 | 2 | 2 | -14 | 83.91% | 75.21% | 19.52% | 88 | Significantly Below Target
ME-0009 | Niger Community Power Project | Kano | Institutional Capacity Building | 37 | 95 | 95 | 1600 | 31 | 208 | 1126 | 88.5% | 3.9 | 58 | 58 | 0 | 100% | 70.38% | 14.9% | 474 | Meeting/Exceeding Target
ME-0010 | Ogun Solar Hub | Kaduna | Institutional Capacity Building | 42 | 87 | 96 | 1836 | 16 | 190 | 1212 | 82.4% | 3.8 | 54 | 54 | 9 | 110.3% | 66.01% | 8.421% | 624 | Meeting/Exceeding Target
ME-0011 | Oyo Solar Water Initiative | Kwara | Solar Water Pump | 44 | 78 | 89 | 644 | 55 | 332 | 517 | 96% | 3.5 | 45 | 45 | 11 | 114.1% | 80.28% | 16.57% | 127 | Meeting/Exceeding Target
ME-0012 | Kaduna Health Power | Ogun | Solar Water Pump | 45 | 78 | 72 | 1886 | 15 | 256 | 1299 | 91.1% | 3.7 | 27 | 27 | -6 | 92.31% | 68.88% | 5.859% | 587 | Moderately Below Target
ME-0013 | Ogun Solar Hub | Kano | Solar Water Pump | 71 | 88 | 78 | 2400 | 35 | 240 | 2279 | 96% | 4.8 | 7 | 7 | -10 | 88.64% | 94.96% | 14.58% | 121 | Moderately Below Target
ME-0014 | Rivers Solar Productive-Use Programme | Delta | Solar Backup System | 66 | 82 | 81 | 271 | 57 | 219 | 249 | 83% | 3.8 | 15 | 15 | -1 | 98.78% | 91.88% | 26.03% | 22 | Moderately Below Target
ME-0015 | Ogun Solar Hub | Oyo | Community Energy Access | 31 | 77 | 71 | 352 | 9 | 166 | 252 | 84.4% | 4.3 | 40 | 40 | -6 | 92.21% | 71.59% | 5.422% | 100 | Moderately Below Target
ME-0016 | Plateau School Energy Project | Kwara | Solar Water Pump | 33 | 91 | 89 | 2304 | 46 | 183 | 2274 | 78.2% | 4.4 | 56 | 56 | -2 | 97.8% | 98.7% | 25.14% | 30 | Moderately Below Target
ME-0017 | Enugu Clean Energy Project | Kaduna | Skills Training | 48 | 95 | 83 | 1799 | 31 | 229 | 1793 | 89.6% | 4.9 | 35 | 35 | -12 | 87.37% | 99.67% | 13.54% | 6 | Significantly Below Target
ME-0018 | Oyo Solar Water Initiative | Kwara | Solar Backup System | 67 | 81 | 72 | 1002 | 12 | 203 | 860 | 81.2% | 4.8 | 5 | 5 | -9 | 88.89% | 85.83% | 5.911% | 142 | Moderately Below Target
ME-0019 | Enugu Clean Energy Project | Oyo | Solar Backup System | 53 | 91 | 99 | 231 | 8 | 214 | 211 | 79.2% | 3.2 | 46 | 46 | 8 | 108.8% | 91.34% | 3.738% | 20 | Meeting/Exceeding Target
ME-0020 | Enugu Clean Energy Project | Anambra | Community Energy Access | 55 | 84 | 87 | 2289 | 53 | 159 | 2216 | 84.7% | 4.4 | 32 | 32 | 3 | 103.6% | 96.81% | 33.33% | 73 | Meeting/Exceeding Target
ME-0021 | Ogun Solar Hub | Plateau | Institutional Capacity Building | 31 | 72 | 59 | 1536 | 65 | 313 | 1365 | 98.4% | 3.4 | 28 | 28 | -13 | 81.94% | 88.87% | 20.77% | 171 | Significantly Below Target
ME-0022 | Enugu Clean Energy Project | Kano | Community Energy Access | 34 | 75 | 52 | 954 | 50 | 110 | 931 | 95.7% | 4.2 | 18 | 18 | -23 | 69.33% | 97.59% | 45.45% | 23 | Significantly Below Target
ME-0023 | Niger Community Power Project | Kano | Solar Water Pump | 39 | 94 | 98 | 1993 | 56 | 330 | 1547 | 80% | 4.2 | 59 | 59 | 4 | 104.3% | 77.62% | 16.97% | 446 | Meeting/Exceeding Target
ME-0024 | Plateau School Energy Project | Enugu | Solar Mini-grid | 31 | 70 | 58 | 439 | 63 | 326 | 386 | 89.4% | 3.4 | 27 | 27 | -12 | 82.86% | 87.93% | 19.33% | 53 | Significantly Below Target
ME-0025 | Oyo Solar Water Initiative | Abia | Community Energy Access | 57 | 95 | 84 | 753 | 34 | 71 | 496 | 89.3% | 3.6 | 27 | 27 | -11 | 88.42% | 65.87% | 47.89% | 257 | Significantly Below Target
ME-0026 | Plateau School Energy Project | Lagos | Solar Mini-grid | 71 | 91 | 94 | 1529 | 24 | 228 | 1034 | 97.3% | 4.5 | 23 | 23 | 3 | 103.3% | 67.63% | 10.53% | 495 | Meeting/Exceeding Target
ME-0027 | Ogun Solar Hub | Delta | Solar Mini-grid | 55 | 82 | 77 | 669 | 48 | 281 | 567 | 81.9% | 3.4 | 22 | 22 | -5 | 93.9% | 84.75% | 17.08% | 102 | Moderately Below Target
ME-0028 | Rivers Solar Productive-Use Programme | Enugu | Community Energy Access | 42 | 86 | 73 | 1348 | 38 | 79 | 932 | 98.1% | 4.4 | 31 | 31 | -13 | 84.88% | 69.14% | 48.1% | 416 | Significantly Below Target
ME-0029 | Enugu Clean Energy Project | Niger | Solar Backup System | 34 | 95 | 79 | 1551 | 21 | 292 | 1511 | 96.2% | 3.6 | 45 | 45 | -16 | 83.16% | 97.42% | 7.192% | 40 | Significantly Below Target
ME-0030 | Niger Community Power Project | Cross River | Solar Water Pump | 72 | 84 | 76 | 1083 | 38 | 119 | 962 | 98.2% | 3.3 | 4 | 4 | -8 | 90.48% | 88.83% | 31.93% | 121 | Moderately Below Target
ME-0031 | Oyo Solar Water Initiative | Abia | Community Energy Access | 46 | 76 | 67 | 879 | 39 | 160 | 734 | 89.6% | 3.7 | 21 | 21 | -9 | 88.16% | 83.5% | 24.38% | 145 | Moderately Below Target
ME-0032 | Kwara SME Solar Programme | Anambra | Solar Water Pump | 45 | 73 | 66 | 508 | 31 | 256 | 456 | 80.1% | 3.7 | 21 | 21 | -7 | 90.41% | 89.76% | 12.11% | 52 | Moderately Below Target
ME-0033 | Enugu Clean Energy Project | Ogun | Community Energy Access | 37 | 76 | 85 | 1561 | 21 | 216 | 1441 | 86.6% | 4 | 48 | 48 | 9 | 111.8% | 92.31% | 9.722% | 120 | Meeting/Exceeding Target
ME-0034 | Niger Community Power Project | Rivers | Community Energy Access | 35 | 93 | 100 | 1737 | 7 | 112 | 1685 | 83.4% | 4.6 | 65 | 65 | 7 | 107.5% | 97.01% | 6.25% | 52 | Meeting/Exceeding Target
ME-0035 | Oyo Solar Water Initiative | Plateau | Solar Backup System | 66 | 79 | 66 | 526 | 70 | 125 | 343 | 99% | 4.8 | 0 | 0 | -13 | 83.54% | 65.21% | 56% | 183 | Significantly Below Target
ME-0036 | Kwara SME Solar Programme | Plateau | Solar Mini-grid | 48 | 74 | 77 | 805 | 73 | 310 | 789 | 86.6% | 4.5 | 29 | 29 | 3 | 104.1% | 98.01% | 23.55% | 16 | Meeting/Exceeding Target
ME-0037 | Kaduna Health Power | Anambra | Solar Mini-grid | 41 | 92 | 64 | 2378 | 76 | 298 | 1600 | 97.1% | 3.9 | 23 | 23 | -28 | 69.57% | 67.28% | 25.5% | 778 | Significantly Below Target
ME-0038 | Kwara SME Solar Programme | Plateau | Institutional Capacity Building | 57 | 71 | 57 | 2495 | 28 | 93 | 2405 | 79.8% | 3.9 | 0 | 0 | -14 | 80.28% | 96.39% | 30.11% | 90 | Significantly Below Target
ME-0039 | Niger Community Power Project | Plateau | Solar Mini-grid | 43 | 72 | 56 | 2226 | 78 | 30 | 2093 | 98.4% | 3.7 | 13 | 13 | -16 | 77.78% | 94.03% | 260% | 133 | Significantly Below Target
ME-0040 | Ogun Solar Hub | Ogun | Institutional Capacity Building | 41 | 94 | 93 | 889 | 57 | 291 | 756 | 86.4% | 3.2 | 52 | 52 | -1 | 98.94% | 85.04% | 19.59% | 133 | Moderately Below Target
ME-0041 | Rivers Solar Productive-Use Programme | Anambra | Solar Mini-grid | 72 | 84 | 88 | 1436 | 7 | 265 | 1206 | 83.9% | 4.4 | 16 | 16 | 4 | 104.8% | 83.98% | 2.642% | 230 | Meeting/Exceeding Target
ME-0042 | Oyo Solar Water Initiative | Cross River | Institutional Capacity Building | 69 | 81 | 69 | 220 | 46 | 36 | 160 | 84.8% | 3.6 | 0 | 0 | -12 | 85.19% | 72.73% | 127.8% | 60 | Significantly Below Target
ME-0043 | Oyo Solar Water Initiative | Niger | Community Energy Access | 45 | 73 | 49 | 155 | 33 | 170 | 112 | 94.2% | 3.3 | 4 | 4 | -24 | 67.12% | 72.26% | 19.41% | 43 | Significantly Below Target
ME-0044 | Plateau School Energy Project | Oyo | Community Energy Access | 44 | 73 | 62 | 1539 | 22 | 125 | 1112 | 84.4% | 4.7 | 18 | 18 | -11 | 84.93% | 72.25% | 17.6% | 427 | Significantly Below Target
ME-0045 | Kwara SME Solar Programme | Delta | Solar Mini-grid | 65 | 71 | 83 | 1029 | 33 | 64 | 790 | 95.3% | 3.6 | 18 | 18 | 12 | 116.9% | 76.77% | 51.56% | 239 | Meeting/Exceeding Target
ME-0046 | Rivers Solar Productive-Use Programme | Kwara | Community Energy Access | 51 | 89 | 76 | 1470 | 39 | 348 | 1073 | 86.8% | 3.6 | 25 | 25 | -13 | 85.39% | 72.99% | 11.21% | 397 | Significantly Below Target
ME-0047 | Enugu Clean Energy Project | Plateau | Skills Training | 61 | 73 | 73 | 357 | 61 | 343 | 265 | 79.7% | 4.9 | 12 | 12 | 0 | 100% | 74.23% | 17.78% | 92 | Meeting/Exceeding Target
ME-0048 | Niger Community Power Project | Oyo | Skills Training | 71 | 72 | 88 | 1956 | 64 | 114 | 1591 | 91.3% | 3.9 | 17 | 17 | 16 | 122.2% | 81.34% | 56.14% | 365 | Meeting/Exceeding Target
ME-0049 | Edo Community Mini-grid | Anambra | Solar Backup System | 53 | 86 | 100 | 324 | 34 | 126 | 242 | 80.8% | 3.4 | 47 | 47 | 14 | 116.3% | 74.69% | 26.98% | 82 | Meeting/Exceeding Target
ME-0050 | Niger Community Power Project | Cross River | Solar Backup System | 41 | 86 | 82 | 1451 | 68 | 66 | 1049 | 94.5% | 3.6 | 41 | 41 | -4 | 95.35% | 72.29% | 103% | 402 | Moderately Below Target
ME-0051 | Oyo Solar Water Initiative | Anambra | Skills Training | 48 | 95 | 85 | 91 | 70 | 302 | 78 | 91% | 4.4 | 37 | 37 | -10 | 89.47% | 85.71% | 23.18% | 13 | Moderately Below Target
ME-0052 | Rivers Solar Productive-Use Programme | Kwara | Institutional Capacity Building | 67 | 94 | 87 | 1199 | 13 | 317 | 877 | 91.4% | 4.5 | 20 | 20 | -7 | 92.55% | 73.14% | 4.101% | 322 | Moderately Below Target
ME-0053 | Plateau School Energy Project | Abia | Institutional Capacity Building | 51 | 94 | 81 | 1577 | 69 | 31 | 1208 | 88% | 3.2 | 30 | 30 | -13 | 86.17% | 76.6% | 222.6% | 369 | Significantly Below Target
ME-0054 | Enugu Clean Energy Project | Kwara | Solar Backup System | 68 | 71 | 79 | 400 | 54 | 143 | 361 | 88.6% | 4.3 | 11 | 11 | 8 | 111.3% | 90.25% | 37.76% | 39 | Meeting/Exceeding Target
ME-0055 | Enugu Clean Energy Project | Ogun | Institutional Capacity Building | 58 | 84 | 81 | 2252 | 27 | 129 | 1534 | 90.9% | 3.8 | 23 | 23 | -3 | 96.43% | 68.12% | 20.93% | 718 | Moderately Below Target
ME-0056 | Rivers Solar Productive-Use Programme | Kwara | Institutional Capacity Building | 74 | 73 | 78 | 2333 | 64 | 236 | 1767 | 96% | 4.2 | 4 | 4 | 5 | 106.8% | 75.74% | 27.12% | 566 | Meeting/Exceeding Target
ME-0057 | Rivers Solar Productive-Use Programme | Kaduna | Solar Water Pump | 61 | 82 | 69 | 1858 | 73 | 106 | 1569 | 85.4% | 3.4 | 8 | 8 | -13 | 84.15% | 84.45% | 68.87% | 289 | Significantly Below Target
ME-0058 | Ogun Solar Hub | Delta | Solar Mini-grid | 73 | 71 | 73 | 2236 | 30 | 123 | 1678 | 84.4% | 4.7 | 0 | 0 | 2 | 102.8% | 75.04% | 24.39% | 558 | Meeting/Exceeding Target
ME-0059 | Plateau School Energy Project | Lagos | Solar Water Pump | 57 | 88 | 97 | 2065 | 48 | 344 | 1623 | 83.2% | 3.4 | 40 | 40 | 9 | 110.2% | 78.6% | 13.95% | 442 | Meeting/Exceeding Target
ME-0060 | Kwara SME Solar Programme | Kaduna | Skills Training | 61 | 80 | 78 | 2038 | 57 | 73 | 1947 | 99.4% | 4.2 | 17 | 17 | -2 | 97.5% | 95.53% | 78.08% | 91 | Moderately Below Target
ME-0061 | Ogun Solar Hub | Edo | Solar Backup System | 30 | 86 | 93 | 87 | 32 | 131 | 60 | 91.6% | 3.4 | 63 | 63 | 7 | 108.1% | 68.97% | 24.43% | 27 | Meeting/Exceeding Target
ME-0062 | Kwara SME Solar Programme | Kwara | Community Energy Access | 38 | 76 | 71 | 1875 | 22 | 121 | 1279 | 94.8% | 4.3 | 33 | 33 | -5 | 93.42% | 68.21% | 18.18% | 596 | Moderately Below Target
ME-0063 | Enugu Clean Energy Project | Anambra | Institutional Capacity Building | 74 | 91 | 79 | 937 | 29 | 318 | 700 | 94.6% | 4.3 | 5 | 5 | -12 | 86.81% | 74.71% | 9.119% | 237 | Significantly Below Target
ME-0064 | Niger Community Power Project | Anambra | Solar Water Pump | 44 | 92 | 80 | 1882 | 29 | 61 | 1763 | 78.9% | 4 | 36 | 36 | -12 | 86.96% | 93.68% | 47.54% | 119 | Significantly Below Target
ME-0065 | Rivers Solar Productive-Use Programme | Kwara | Institutional Capacity Building | 67 | 86 | 90 | 1335 | 75 | 71 | 1208 | 85.8% | 4.3 | 23 | 23 | 4 | 104.7% | 90.49% | 105.6% | 127 | Meeting/Exceeding Target
ME-0066 | Kwara SME Solar Programme | Anambra | Solar Mini-grid | 55 | 75 | 73 | 1981 | 15 | 70 | 1919 | 78.5% | 3.7 | 18 | 18 | -2 | 97.33% | 96.87% | 21.43% | 62 | Moderately Below Target
ME-0067 | Enugu Clean Energy Project | Plateau | Community Energy Access | 33 | 80 | 78 | 1737 | 14 | 234 | 1609 | 84.8% | 4.2 | 45 | 45 | -2 | 97.5% | 92.63% | 5.983% | 128 | Moderately Below Target
ME-0068 | Enugu Clean Energy Project | Plateau | Solar Backup System | 58 | 88 | 88 | 2461 | 38 | 305 | 2029 | 80.3% | 3.4 | 30 | 30 | 0 | 100% | 82.45% | 12.46% | 432 | Meeting/Exceeding Target
ME-0069 | Kwara SME Solar Programme | Abia | Community Energy Access | 44 | 83 | 76 | 586 | 50 | 200 | 471 | 91.9% | 3.3 | 32 | 32 | -7 | 91.57% | 80.38% | 25% | 115 | Moderately Below Target
ME-0070 | Niger Community Power Project | Niger | Solar Mini-grid | 36 | 91 | 96 | 1952 | 44 | 349 | 1594 | 90.9% | 4.2 | 60 | 60 | 5 | 105.5% | 81.66% | 12.61% | 358 | Meeting/Exceeding Target
ME-0071 | Rivers Solar Productive-Use Programme | Kwara | Solar Water Pump | 62 | 70 | 70 | 1619 | 20 | 151 | 1170 | 79.3% | 4.1 | 8 | 8 | 0 | 100% | 72.27% | 13.25% | 449 | Meeting/Exceeding Target
ME-0072 | Edo Community Mini-grid | Abia | Solar Mini-grid | 64 | 77 | 64 | 999 | 39 | 263 | 677 | 90.2% | 4.7 | 0 | 0 | -13 | 83.12% | 67.77% | 14.83% | 322 | Significantly Below Target
ME-0073 | Edo Community Mini-grid | Anambra | Skills Training | 58 | 85 | 91 | 2387 | 40 | 36 | 1989 | 84.9% | 4 | 33 | 33 | 6 | 107.1% | 83.33% | 111.1% | 398 | Meeting/Exceeding Target
ME-0074 | Enugu Clean Energy Project | Rivers | Skills Training | 59 | 91 | 88 | 1169 | 15 | 241 | 907 | 84.6% | 3.5 | 29 | 29 | -3 | 96.7% | 77.59% | 6.224% | 262 | Moderately Below Target
ME-0075 | Ogun Solar Hub | Niger | Solar Backup System | 52 | 95 | 96 | 1815 | 27 | 105 | 1478 | 87.1% | 4.9 | 44 | 44 | 1 | 101.1% | 81.43% | 25.71% | 337 | Meeting/Exceeding Target
ME-0076 | Enugu Clean Energy Project | Lagos | Solar Backup System | 39 | 74 | 61 | 1627 | 30 | 265 | 1106 | 95.5% | 3.7 | 22 | 22 | -13 | 82.43% | 67.98% | 11.32% | 521 | Significantly Below Target
ME-0077 | Plateau School Energy Project | Kwara | Solar Backup System | 68 | 90 | 84 | 501 | 40 | 205 | 403 | 79% | 4.6 | 16 | 16 | -6 | 93.33% | 80.44% | 19.51% | 98 | Moderately Below Target
ME-0078 | Kwara SME Solar Programme | Ogun | Solar Water Pump | 33 | 86 | 68 | 1201 | 25 | 191 | 1173 | 88% | 4 | 35 | 35 | -18 | 79.07% | 97.67% | 13.09% | 28 | Significantly Below Target
ME-0079 | Plateau School Energy Project | Cross River | Solar Water Pump | 43 | 76 | 58 | 1734 | 52 | 284 | 1139 | 95.6% | 4.6 | 15 | 15 | -18 | 76.32% | 65.69% | 18.31% | 595 | Significantly Below Target
ME-0080 | Plateau School Energy Project | Edo | Solar Backup System | 61 | 79 | 80 | 969 | 18 | 142 | 685 | 82% | 3.5 | 19 | 19 | 1 | 101.3% | 70.69% | 12.68% | 284 | Meeting/Exceeding Target

## Pre-Analysis
Project Split
Dependent Variables
1. Record_ID
2. Baseline_% Target_% 3.Current_Achievement_% 4.Beneficiaries Local_Jobs_Created 5.People_Trained 6.People_Gaining_Clean_Energy_Access
7.System_Uptime_% 8.Community_Satisfaction
9.Achievement_Gap_pp
10. Target_Gap_pp
Independent Variables
1. Project
2. State
3. Intervention
4. Performance Status
Potential Data Story
Which interventions are meeting their targets, where are impact gaps occurring, and what operational factors are associated with stronger community outcomes?
Tool Used
Industry
Renewable Energy + Monitoring & Evaluation
Microsoft Excel
What Success Mean to the Industry
Delivering reliable clean energy that creates measurable economic and social value for communities while meeting programme targets.
StakeHolders
1. Executive Management: Overall intervention Performance and impact
2. M & E Team: Whether programmes are achieiving targets
3. HR/Training Team: People trained and employment outcomes
4. Host Communities: Reliable electricity, jobs and skills
5 Investors: ESG and community-impact performance
Potential Business Questions
Which interventions and states are meeting their targets, and where are the largest performance gaps?
2. How effectively are interventions translating into meaningful clean-energy access for beneficiaries?
3. What relationship exists between system reliability and community satisfaction?
4. Are skills-development initiatives translating into local employment opportunities?
5. Which interventions demonstrate the strongest overall community impact?
Potential Insights
1. Some interventions may already be exceeding targets, creating potential models for practices that could be replicated elsewhere.
2. Some interventions may have large beneficiary numbers but relatively low clean-energy access.
3. Higher system uptime may be associated with higher community satisfaction.
4. High training + low jobs could indicate a gap between skills development and actual economic opportunity.
5. Strong-performing interventions may share a combination of high target achievement, reliable systems, strong clean-energy access and high satisfaction.

## Calculations
Calculated Columns
Name | Purpose | Formula
Achievement Gap | How much has performance improved from baseline? | Current_Achievement_% - Baseline_%
Target Gap | How far is current performance from the target? | Current_Achievement_% - Target_%
Target Achievement Rate | How much of the target has been achieved | Current_Achievement_% / Target_%
Clean Energy Access Rate | What proportion of beneficiaries are actually gaining clean-energy access? | People_Gaining_Clean_Energy_Access / Beneficiaries
Training-to-Employment Rate | Is skills development translating into local employment? | Local_Jobs_Created / People_Trained
Unserved Beneficiaries | Beneficiaries who are not currently recorded as gaining clean-energy access. | Beneficiaries - People_Gaining_Clean_Energy_Access
Performance Status | Who's meeting target, exceeding or underperforming? | Nested if statements

## Chart
1. Which interventions/states are missing their targets? |  | 2. Are beneficiaries actually gaining clean-energy access? | [5 empty] | KPIs
[8 empty] | Target Achievement Rate | 95.09%
Row Labels | Sum of Target_Gap | Row Labels | Sum of Beneficiaries | Sum of People_Gaining_Clean_Energy_Access | 5. Which interventions demonstrate the strongest overall performance? |  |  | Target Gap | -35
Ogun | -19 | Anambra | 16578 | 13850 | Row Labels | Count of Performance Status |  | Clean-Energy Access | 56667
Lagos | -18 | Kwara | 14682 | 11789 | Community Energy Access | 17 |  | System Uptime % | 88.35%
Kwara | -14 | Plateau | 12143 | 10898 | Solar Backup System | 15 |  | Community Satisfaction | 4.0337
Enugu | -10 | Kaduna | 9056 | 7968 | Solar Water Pump | 15 |  | Training-to-Employment Rate | 34.5%
Edo | 2 | Ogun | 7789 | 6203 | Solar Mini-grid | 12
Rivers | 4 | Lagos | 7549 | 5959 | Institutional Capacity Building | 12 |  | Today | 4629000%
Oyo | 7 | Grand Total | 67797 | 56667 | Skills Training | 9 |  |  | 25 Sep 2026
Delta | 13 |  |  |  | Grand Total | 80
Grand Total | -35
0
6. Community Impact Profile
[5 empty] | Row Labels | Average of Target_Achievement_Rate | Average of Clean_Energy _Access_Rate | Average of System_Uptime_% | Average of Community_Satisfaction
[5 empty] | Community Energy Access | 90.2% | 82.01% | 88.29% | 4.1706
[5 empty] | Institutional Capacity Building | 94.18% | 78.18% | 88.92% | 3.8417
[5 empty] | Skills Training | 100.7% | 86.39% | 88.62% | 4.2222
[5 empty] | Solar Backup System | 97.64% | 80.61% | 87.51% | 3.98
[5 empty] | Solar Mini-grid | 95.16% | 81.81% | 89.49% | 4.0583
[5 empty] | Solar Water Pump | 95.39% | 83.04% | 87.73% | 3.9533
4. Is training translating into local jobs? |  | 3. Does reliability relate to community satisfaction? |  |  | Grand Total | 95.09% | 81.83% | 88.35% | 4.0337
Row Labels | Sum of Local_Jobs_Created | Row Labels | Sum of Community_Satisfaction
30 | 78 | 78.2% | 4.4
31 | 69 | 78.5% | 3.7
36 | 86 | 78.9% | 4
37 | 51 | 79% | 4.6 |  | Row Labels | Average of Training-to-Employment_Rate |  |  | Row Labels | Average of Target_Achievement_Rate | Average of Clean_Energy _Access_Rate | Average of System_Uptime_%
57 | 66 | 79.2% | 3.2 |  | Community Energy Access | 28.54% |  |  | Anambra | 97.01% | 83.45% | 86.48%
61 | 29 | 79.3% | 4.1 |  | Institutional Capacity Building | 50.92% |  |  | Delta | 103.6% | 84.1% | 85.6%
64 | 33 | 79.7% | 4.9 |  | Skills Training | 37.63% |  |  | Edo | 100.6% | 76% | 89.43%
66 | 68 | 79.8% | 3.9 |  | Solar Backup System | 34.04% |  |  | Enugu | 95.74% | 80.77% | 92%
70 | 15 | 80% | 4.2 |  | Solar Mini-grid | 40.29% |  |  | Kwara | 98.93% | 80.76% | 87.01%
71 | 109 | 80.1% | 3.7 |  | Solar Water Pump | 22.08% |  |  | Oyo | 102% | 79.13% | 84.82%
73 | 57 | 80.3% | 3.4 |  | Grand Total | 34.5% |  |  | Rivers | 102.1% | 87.3% | 84%
79 | 38 | 80.8% | 3.4 | [5 empty] | Grand Total | 99.35% | 81.75% | 86.87%
93 | 28 | 81.2% | 4.8
96 | 9 | 81.9% | 3.4
105 | 27 | 82% | 3.5
106 | 73 | 82.4% | 3.8
110 | 50 | 83% | 3.8
112 | 7 | 83.1% | 4.8
114 | 64 | 83.2% | 3.4
119 | 38 | 83.4% | 9.4
121 | 22 | 83.9% | 4.4
123 | 30 | 84.4% | 13.7
125 | 92 | 84.6% | 3.5
126 | 34 | 84.7% | 4.4
129 | 27 | 84.8% | 7.8
131 | 59 | 84.9% | 4
142 | 18 | 85.4% | 3.4
143 | 54 | 85.8% | 9
151 | 20 | 86.4% | 3.2
159 | 53 | 86.6% | 8.5
160 | 39 | 86.8% | 3.6
166 | 9 | 87.1% | 4.9
170 | 33 | 88% | 7.2
183 | 46 | 88.5% | 8.2
190 | 16 | 88.6% | 8.2
191 | 25 | 89.2% | 4.2
200 | 50 | 89.3% | 3.6
203 | 12 | 89.4% | 3.4
204 | 65 | 89.6% | 8.6
205 | 40 | 90.2% | 4.7
208 | 31 | 90.9% | 8
214 | 8 | 91% | 4.4
216 | 21 | 91.1% | 3.7
219 | 57 | 91.3% | 3.9
228 | 24 | 91.4% | 4.5
229 | 31 | 91.6% | 3.4
234 | 14 | 91.9% | 3.3
236 | 64 | 94.2% | 3.3
240 | 35 | 94.5% | 3.6
241 | 71 | 94.6% | 4.3
256 | 46 | 94.7% | 4.7
263 | 39 | 94.8% | 4.3
265 | 37 | 95.3% | 3.6
273 | 34 | 95.5% | 3.7
281 | 48 | 95.6% | 4.6
284 | 52 | 95.7% | 4.2
291 | 57 | 96% | 12.5
292 | 78 | 96.2% | 3.6
298 | 76 | 96.8% | 4
302 | 70 | 97.1% | 3.9
305 | 38 | 97.3% | 4.5
310 | 73 | 98.1% | 4.4
313 | 65 | 98.2% | 3.3
317 | 13 | 98.4% | 7.1
318 | 29 | 99% | 4.8
326 | 63 | 99.4% | 4.2
330 | 56 | Grand Total | 322.7
332 | 55
343 | 61 | Row Labels | Sum of Community_Satisfaction
344 | 48 | 78.2% | 4.4
348 | 39 | 78.5% | 3.7
349 | 44 | 78.9% | 4
Grand Total | 3216 | 79% | 4.6
|  | 79.2% | 3.2
|  | 79.3% | 4.1
|  | 79.7% | 4.9
30 | 78 | 79.8% | 3.9
31 | 69 | 80% | 4.2
36 | 86 | 80.1% | 3.7
37 | 51 | 80.3% | 3.4
57 | 66 | 80.8% | 3.4
61 | 29 | 81.2% | 4.8
64 | 33 | 81.9% | 3.4
66 | 68 | 82% | 3.5
70 | 15 | 82.4% | 3.8
71 | 109 | 83% | 3.8
73 | 57 | 83.1% | 4.8
79 | 38 | 83.2% | 3.4
93 | 28 | 83.4% | 9.4
96 | 9 | 83.9% | 4.4
105 | 27 | 84.4% | 13.7
106 | 73 | 84.6% | 3.5
110 | 50 | 84.7% | 4.4
112 | 7 | 84.8% | 7.8
114 | 64 | 84.9% | 4
119 | 38 | 85.4% | 3.4
121 | 22 | 85.8% | 9
123 | 30 | 86.4% | 3.2
125 | 92 | 86.6% | 8.5
126 | 34 | 86.8% | 3.6
129 | 27 | 87.1% | 4.9
131 | 59 | 88% | 7.2
142 | 18 | 88.5% | 8.2
143 | 54 | 88.6% | 8.2
151 | 20 | 89.2% | 4.2
159 | 53 | 89.3% | 3.6
160 | 39 | 89.4% | 3.4
166 | 9 | 89.6% | 8.6
170 | 33 | 90.2% | 4.7
183 | 46 | 90.9% | 8
190 | 16 | 91% | 4.4
191 | 25 | 91.1% | 3.7
200 | 50 | 91.3% | 3.9
203 | 12 | 91.4% | 4.5
204 | 65 | 91.6% | 3.4
205 | 40 | 91.9% | 3.3
208 | 31 | 94.2% | 3.3
214 | 8 | 94.5% | 3.6
216 | 21 | 94.6% | 4.3
219 | 57 | 94.7% | 4.7
228 | 24 | 94.8% | 4.3
229 | 31 | 95.3% | 3.6
234 | 14 | 95.5% | 3.7
236 | 64 | 95.6% | 4.6
240 | 35 | 95.7% | 4.2
241 | 71 | 96% | 12.5
256 | 46 | 96.2% | 3.6
263 | 39 | 96.8% | 4
265 | 37 | 97.1% | 3.9
273 | 34 | 97.3% | 4.5
281 | 48 | 98.1% | 4.4
284 | 52 | 98.2% | 3.3
291 | 57 | 98.4% | 7.1
292 | 78 | 99% | 4.8
298 | 76 | 99.4% | 4.2
302 | 70
305 | 38
310 | 73
313 | 65
317 | 13
318 | 29
326 | 63
330 | 56
332 | 55
343 | 61
344 | 48
348 | 39
349 | 44

## Dashboard
Renewable Energy & Community Impact Dashboard
Tracking Performance. Measuring Impact. Powering Sustainable Change
Last Updated
25 Sep 2026
Ferrouz
Clean Energy Plus Impact for Change
Overview
Performance
Energy Access
Communities
Reports
Dataset
Target Achievement Rate
Target Gap
Access to Clean Energy
System Uptime
Community Satisfaction
Training-to-Employment Rate
95.09%
-35
56.7K
88.35%
4.03
34.50%
Where are We Missing Targets?
Target Group By State
Insight: The performance gap is concentrated in four states, with Ogun and Lagos requiring the closest attention due to their larger shortfalls.
Are Beneficiaries Gaining Clean-Energy Access?
Beneficiaries Vs. People Gaining Clean Energy Access
Insight: Clean-energy interventions are reaching beneficiaries, but access gaps remain across all six states, highlighting last-mile delivery challenges.
Beneficiaries
People Gaining Clean Energy Access
Does Reliability Relate to Satisfaction?
System Uptime Vs. Community Satisfaction
Insight: Reliability appears to support community satisfaction, but reliability alone does not fully explain satisfaction levels.
Is Training Translating into Jobs?
People Trained Vs. Local Jobs Created
Insight: Training is creating local jobs, but the number of jobs created varies widely across interventions.
Which Interventions are Performing Well?
Performance Status By Intervention
Insight: Energy-focused interventions are currently showing the strongest overall performance.
What Does Strong Community Impact Look Like?
Key Outcomes By State (Percentage)
Insight: Impact is generally strong, but different states lead on different measures, suggesting room to strengthen weaker areas.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## In-Analysis
In Analysis Observations
1. Which interventions/states are missing their targets?
Ogun records the largest target shortfall at 19 units, followed by Lagos (18), Kwara (14), and Enugu (10). Together, these four states account for a total shortfall of 61 units, indicating where intervention efforts may need to be prioritised.
By contrast, Delta (+13), Oyo (+7), Rivers (+4), and Edo (+2) are exceeding their targets.
2. Are beneficiaries actually gaining clean-energy access?
Across the six states, actual clean-energy access falls below the number of beneficiaries in every case, indicating that not all identified beneficiaries are currently gaining access.
A. Anambra has the largest reach in absolute terms, with 13.9K beneficiaries gaining access out of 16.6K.
B. Plateau shows the strongest coverage, with 10.9K of 12.1K beneficiaries reached.
C. Ogun and Lagos have relatively larger access gaps, with 1.6K and 1.5K beneficiaries respectively yet to gain access.
3. Does reliability relate to community satisfaction?
Community satisfaction tends to be higher at stronger reliability levels, with several satisfaction scores above 7 appearing at reliability levels of 84% and above. However, the relationship is not consistent, as some highly reliable communities still report satisfaction scores around 3–4.
4. Is training translating into local jobs?
Higher training levels do not consistently translate into more local jobs. For example, 71 training participants generated 109 jobs, while 96 generated only 9.
5. Which interventions demonstrate the strongest overall performance?
Community Energy Access leads with 17, followed by Solar Backup System and Solar Water Pump at 15 each. Skills Training records the lowest score at 9.
6. Community Impact Profile
Most states show strong performance across the three impact measures, but the results vary by state. Rivers has the highest second metric (87.3%), while Enugu leads the third metric (92%). Delta records the highest first metric at 103.57%.
1. Prioritise underperforming states Focus immediate support on Ogun, Lagos, Kwara and Enugu, where beneficiary targets are below expectations.
2. Close clean-energy access gaps Strengthen last-mile delivery to ensure more identified beneficiaries actually receive clean-energy access.
3. Improve reliability and service quality Address reliability issues in communities with lower satisfaction to improve the overall user experience.
4. Strengthen post-training job placement Link skills training to local employers, contractors and project opportunities to improve job creation.
5. Scale high-performing energy interventions Consider expanding interventions such as Community Energy Access, Solar Backup Systems and Solar Water Pumps, which recorded the strongest performance scores.
6. Target state-specific weaknesses Since states perform differently across the impact measures, use state-level data to identify and address specific gaps rather than applying the same intervention strategy everywhere.
In Analysis Recommendations

## Final Recommendations
Final StakeHolder Recommendations
Based on the analysis, I would recommend the following actions:
1. I would prioritise Ogun, Lagos, Kwara and Enugu for targeted intervention. These states are currently below their beneficiary targets, so I would first identify the specific delivery gaps in each state before allocating additional resources.
2. I would focus on closing the gap between beneficiaries and actual clean-energy access. Rather than only tracking how many people are registered as beneficiaries, I would track how many have actually received and are using the energy solution. This would make last-mile delivery a clear performance measure.
3. I would strengthen post-training job placement. Since training does not consistently result in local jobs, I would connect trainees with local installers, contractors, suppliers and project teams. I would also track how many trainees secure work after completing each programme.
4. I would improve reliability where community satisfaction is low. I would use community feedback alongside reliability data to identify locations where equipment downtime or service interruptions are affecting satisfaction, then prioritise those locations for maintenance.
5. I would expand interventions that are already performing well. I would consider scaling Community Energy Access, Solar Backup Systems and Solar Water Pumps, while continuing to monitor their results to ensure expansion maintains the same level of impact.
6. I would manage each state based on its specific performance gaps. Rather than using one approach across all communities, I would use the dashboard to identify whether each state needs more focus on energy access, reliability, training, employment or community satisfaction.
7. I would introduce a simple monthly impact review. I would track a small set of KPIs; target achievement, clean-energy access, reliability, community satisfaction and local jobs created and use the results to decide where resources and corrective actions are needed each month.
Overall recommendation
I would move the programme from measuring activities to measuring outcomes: not just how many people we train or target, but how many actually gain energy access, experience reliable service, find local employment and report improved community outcomes.